## Sheet1
No | Item | Remark | Status | Is isolate? (Mc No)
1 | The LSF Measurement by cluster. | 23/9 KN: Support LSF Cluster Mode | Pending Test
2 | 3999 Do_Vision Out of Memory. | 20/9 KN lets monitor by machine. | Further Monitoring
3 | Unload timeout, retry check magazine is psnt. | 20/9 KN Added mag check for retry. | Pending UCD Verification
4 | Z Axis jog down, some time not stop | 23/9 KN: Code change to Async for GZN MouseDown, free UI thread to process GZN MouseUp. | Pending UCD Verification
5 | Mag Level need to match Elev Setup Mag Count | 20/9 KN Corrected display. | Pending UCD Verification
6 | Continue Run, Correct Tower Light Yellow due to Do_Vision state | 20/9 KN Refactor all Tower Light States | Pending UCD Verification
7 | BGT017 Software freese during Setup | 20/9 KN futher monitoring needed. Old mc. | Further Monitoring | BGT017
8 | 3999 Not enough storage is available to process this command | 20/9 KN Is this machine specific? | Further Monitoring
9 | BSD008 Software freeze during scanning | 20/9 KN futher monitoring needed. Old mc. | Further Monitoring | BGT008
10 | Z Touch Encoder Down Count fail. | 20/9 KN this should be machine specific not software. The touch module may need maintainance. | Pending Test
11 | After EMO, software freeze and need to restart. | 20/9 KN Is this machine specific? | Further Monitoring
12 | BSD018 dispense complete, support plate down, panel not transfer to out and alarm conv timeout. | 20/9 KN this should be machine specific not software. | Need local resolution | BGT018
13 | 2D License lost after upgrading software? | 20/9 KN supplier communication was added. | Replied by Supplier
14 | Enable Process Log to to as local. | 20/9 KN Updated to machine. | Pending UCD Verification
15 | Correct DispProg.Setting recipe name display. | 4/9 KN 6.1.5.5 Display corrent recipe name. | Pending UCD Verification
16 | Disable Map Edit | 23/9 KN: Diable Map Edit during Auto Run. | Pending UCD Verification

## Isolated Tracking
Date/Time | McNo | PIC | Description | Error (if any) | Observation | Remark
?? | ?? |  |  | 3999 Do_Vision Out of Memory.
?? | BGT017 |  |  | BGT017 Software freese during Setup
?? | BGT008 |  |  | BSD008 Software freeze during scanning
?? | ?? |  | Z Touch Encoder Down Count fail.
?? | ?? |  | After EMO, software freeze and need to restart.
?? | BGT018 |  | BSD018 dispense complete, support plate down, panel not transfer to out and alarm conv timeout.